| Church Development Plan for St John’s, Farncombe |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Adopted by the PCC |  |  |  |  |  | Review date |  |  |  |  |  |
| # | Priority | Local principle | Diocesan goal | Specific action points | Steps |  | Owner | Resources needed | To be achieved by | Review by |
| 1 | Improving communication | ‘This church wants to share Christ’ | Making disciples/ Increasing believers/ Communicating effectively | Recruiting social media/photography person or team | Announce recruitment and identify person/team |  | JR | Newsletters, email, people | Spring 2027 | Autumn 2026 |
|  |  |  |  |  | Set goals and implement |  | JR/team | People | Spring 2027 | Autumn 2026 |
|  |  |  |  | Making more use of visiting contacts/Messy Church/Toddlers | Keeping records |  | JR | Mailing lists, visiting time | Autumn 2026 | Summer 2026 |
|  |  |  |  |  | Identifying interests |  |  |  |  |  |
|  |  |  |  |  | Publicising events and next steps as appropriate |  |  |  |  |  |
| 2 | Improving the means by which people move forward in their Christian lives | ‘This church seeks more of Christ’ | Making disciples | Establishing effective pathways from events/groups | Identify responsible people |  | JR |  | Summer 2026 | Summer 2026 |
|  |  |  |  |  | Responsible people to examine pathways |  | Team |  | Summer 2026 |  |
|  |  |  |  |  | Report |  |  |  | Winter 2026 |  |
| 3 | Considering how to make our worship deeper | ‘This church wants to share Christ’ ‘This church seeks more of Christ’ ‘This church gives God the best’ | Increasing believers | Deciding on AV system | Identify subgroup |  | JR |  | Summer 2026 | Summer 2026 |
|  |  |  |  |  | Responsible people to examine options |  | Team |  | Autumn 2026 |  |
|  |  |  |  |  | Report |  |  |  | Winter 2026 |  |
|  |  |  |  | Deciding on music provision | Identify subgroup |  | JR |  | Summer 2026 | Summer 2026 |
|  |  |  |  |  | Responsible people to examine options |  | Team |  | Autumn 2026 |  |
|  |  |  |  |  | Report |  |  |  | Spring 2027 |  |
| 4 | Rethinking outreach | ‘This church wants to share Christ’ | Increasing believers | Considering youth provision | Discussion with team |  | JR/team |  | Summer 2026 | Summer 2026 |
|  |  |  |  |  | Discussion with YPs |  | JR/team |  | Autumn 2026 |  |
|  |  |  |  | Considering work with commuters | JR to investigate |  | JR |  | Summer 2026 | Summer 2026 |
| 5 | Community service | ‘This church loves God’s world’ | Reaching beyond borders/ Community partnerships | Business lunch | JR to investigate |  | JR |  | Autumn 2026 | Summer 2026 |
|  |  |  |  | Eco church | JR meeting with Alison Moulden |  | JR |  | Autumn 2026 | Summer 2026 |
|  |  |  |  |  | Recruit team |  | DP |  |  |  |
|  |  |  |  | Establish new pastoral team | JR to meet with PAs and others |  | JR/PAs |  | Autumn 2026 | Summer 2026 |